## Workflow Tracker
| Timeline anchor (edit to shift all seeded dates) → | 2026-07-27
Recruitment Workflow Tracker
One row per stage of the hiring process. Update Status as work progresses — the Days Left and Flag columns update themselves.
Recruitment Stage | Owner | Target Date | Status | Days Left | Flag | Notes
Hiring request raised | Hiring Manager | 2026-07-15 | Completed |  | Done | Approved by Finance
Budget & headcount approved | Finance | 2026-07-16 | Completed |  | Done | Band confirmed at $90k–$110k
Job description finalised | Recruiter | 2026-07-18 | Completed |  | Done | Reviewed by hiring manager
Job published to channels | Recruiter | 2026-07-19 | Completed |  | Done | Posted to LinkedIn and careers page
Candidate sourcing | Recruiter | 2026-07-25 | In Progress | -2 | Overdue | 120 profiles sourced so far
Resume screening | Recruiter | 2026-07-29 | Pending | 2 | Due now
HR screening calls | HR | 2026-08-01 | Pending | 5 | On track
Technical interviews | Engineering Team | 2026-08-04 | Pending | 8 | On track
Final interview | Hiring Manager | 2026-08-07 | Pending | 11 | On track
Reference checks | HR | 2026-08-09 | Pending | 13 | On track
Offer approved internally | Hiring Manager | 2026-08-11 | Pending | 15 | On track
Offer sent to candidate | HR | 2026-08-13 | Pending | 17 | On track
Offer accepted | HR | 2026-08-16 | Pending | 20 | On track
Pre-boarding & documentation | HR | 2026-08-20 | Pending | 24 | On track
Candidate joined | HR | 2026-08-26 | Pending | 30 | On track
PROGRESS SUMMARY
Metric | Value
Stages defined | 15
Completed | 4
In progress | 1
Pending | 10
Blocked | 0
Overdue | 1
% complete | 26.67%
HOW TO USE THIS SHEET
• Yellow cells with blue text are the ones you fill in. Everything else is calculated for you — do not overwrite it.
• Row(s) marked EXAMPLE show the expected format. Delete them once you have entered your own data.
• Cells with a dropdown arrow accept only the listed values; the calculations depend on those exact words.
• Flag is automatic: Overdue means the target date has passed and the stage is not marked Completed.
• Add or rename stages freely — the summary counts adjust to whatever you enter in the Recruitment Stage column.
Free recruitment workflow template · Leelu AI · Sample data shown is illustrative only and is not drawn from any real hiring campaign.
Formulas:
Target Date = IF([Recruitment Stage]="","",D1+(-12))
Target Date = IF([Recruitment Stage]="","",D1+(2))
Days Left = IF(OR([Recruitment Stage]="",[Target Date]=""),"",IF([Status]="Completed","",[Target Date]-TODAY()))
Flag = IF([Recruitment Stage]="","",IF([Status]="Completed","Done",IF([Status]="Blocked","Blocked",IF([Target Date]="","No date",IF([Target Date]<TODAY(),"Overdue",IF([Target Date]-TODAY()<=2,"Due now","On track"))))))